## ProjectName
Application | # | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Airline Reservation System | 1 | Analysis | Requirement Analysis | 1 | 2017-03-03 | 2017-03-03 | 1 | 2017-03-03 | 2017-03-03 | Rajat Bhutani, Jeeveswar Medavaram | Completed
|  |  | Preparing understanding document | 1 | 2017-03-03 | 2017-03-03 | 1 | 2017-03-03 | 2017-03-03 | Farah Jamal | Completed
|  |  | Updating QTS | 1 | 2017-03-03 | 2017-03-03 | 0.5 | 2017-03-03 | 2017-03-03 | Rajat Bhutani | Completed
|  |  | Understanding HLD/Class Diagram Prep | 2 | 2017-03-03 | 2017-03-03 | 2 | 2017-03-03 | 2017-03-03 | Ritika Mishra,Farah Jamal,Jeeveswar | Completed
|  | Design | Unit Test Plan Preparation | 1 | 2017-03-04 | 2017-03-04 | 1.5 | 2017-03-04 | 2017-03-04 | Priya Kaushik | Completed
|  |  | LLD Preparation | 3 | 2017-03-07 | 2017-03-07 | 3 | 2017-03-07 | 2017-03-07 | Ritika Mishra | Completed
|  |  | UTP Review | 0.5 | 2017-03-06 | 2017-03-07 | 0.5 | 2017-03-06 | 2017-03-06 | Rajat Bhutani | Completed
|  |  | UTP Rework | 1 | 2017-03-07 | 2017-03-07 | 1 | 2017-03-07 | 2017-03-07 | Priya Kaushik | Completed
|  |  | LLD Review | 1 | 2017-03-07 | 2017-03-07 | 1 | 2017-03-07 | 2017-03-07 | Rajat Bhutani | Completed
|  | Build | Coding | 6 | 2017-03-08 | 2017-03-08 | 6 | 2017-03-08 | 2017-03-08 | Rajat Aggarwal | Completed
|  |  | Code Self Review | 3 | 2017-03-08 | 2017-03-08 | 3 | 2017-03-08 | 2017-03-08 | Rajat Bhutani | Completed
|  |  | Self Testing | 2 | 2017-03-09 | 2017-03-09 | 2 | 2017-03-09 | 2017-03-09 | Priya Kaushik | Completed
|  |  | Rework | 3 | 2017-03-10 | 2017-03-10 | 3 | 2017-03-10 | 2017-03-10 | Rajat Aggarwal | Completed
|  |  | Code Peer Review | 4 | 2017-03-10 | 2017-03-10 | 4 | 2017-03-10 | 2017-03-10 | Rajat Bhutani | Completed
|  |  | Peer Testing | 5 | 2017-03-10 | 2017-03-10 | 5 | 2017-03-10 | 2017-03-10 | Priya Kaushik | Completed
|  |  | Test Result review | 2 | 2017-03-11 | 2017-03-11 | 2 | 2017-03-11 | 2017-03-11 | Ritika Mishra | Completed
|  |  | Rework | 1 | 2017-03-13 | 2017-03-13 | 1 | 2017-03-13 | 2017-03-13 | Rajat Bhutani | Completed
|  |  | Code Integration | 2 | 2017-03-13 | 2017-03-13 | 2 | 2017-03-13 | 2017-03-13 | Rabina Chand | Completed
|  |  | Integration Testing | 1 | 2017-03-13 | 2017-03-13 | 1 | 2017-03-13 | 2017-03-13 | Rajat Aggarwal | Completed
|  |  | Rework | 1 | 2017-03-14 | 2017-03-14 | 1 | 2017-03-14 | 2017-03-14 | Rabina Chand | Completed
|  |  | Test Result review | 1 | 2017-03-14 | 2017-03-14 | 1 | 2017-03-14 | 2017-03-14 | Rajat Bhutani | Completed
|  |  | Total Planned Hrs : |  |  | Total Actual Hrs: | 41.5